Milestone Language

By September 30, 2026, gather and document details necessary (e.g., use case, state of the art, bathymetry, inflow) to motivate and perform a simulation of an estuary flow under conditions for which field measurements exist. Perform high-fidelity simulation of estuary flow to investigate the flow/current structures that are resolved that would inform turbine siting.
Validate the capability against field measurements, and document any advantages compared to a regional-scale model typically used, e.g., FVCOM

With Turbine

Milestone run, functional description:

- AMR-Wind will read in mesoscale flow from precursor FVCOM simulation, informing the velocity and volume fraction (and thereby, density) fields at the boundary.

- AMR-Wind will model bathymetry using the existing immersed boundary forcing method (IBFM). The wall effects will be handled using existing LES-compatible wall models.

- AMR-Wind will represent the turbine and any associated structures using actuator-based methods, coupled with Kynema to calculate the structural dynamics.

- Kynema will calculate the forces on the turbine and any associated structures with its aerodynamics module, which will include added mass effects due to the high density of water.

Required capabilities that need to be implemented or used in novel ways:

- Method to read in mesoscale precursor data and read in as boundary planes in non-ABL simulation.

  - Write tool to convert FVCOM data to boundary plane format used for time- and space-varying input to AMR-Wind – Matt

  - Refactor boundary plane implementation in AMR-Wind to be used outside of ABL physics – Michael

- Method to apply phase-aware and bathymetry-aware initial and boundary conditions outside of OceanWaves physics (intended for wave forcing)

  - Implement phase-aware and terrain-aware options for boundary plane fill (adapt from ocean waves fill)

  - Implement two-phase initialization that reads in an initial state for the flow; potentially also could calculate a reasonable starting point

- For validation of the wall model with bathymetry, an underwater source term, similar to ABLForcing, would need to be added to spin up turbulence in a precursor simulation

- If any non-turbine bodies are modeled, a method to set up these Kynema components will need to be added to AMR-Wind

- Added mass capabilities added to Kynema aerodynamics module

Capabilities that would need validation or verification:

- Immersed Boundary Forcing Method (IBFM)

  - Flat boundary case – laminar

  - Non-flat boundary case – laminar

  - Flat boundary case – using wall model

  - Non-flat boundary case – using wall model

- IBFM for underwater flows

  - Simple channel – laminar

  - Simple channel – using wall model

  - Complex channel – using wall model

- Current and sea surface rise

- Kynema added mass aero

Expected additional hurdles:

- Need for optimizing domain size, number of cells, and pressure solver options due to the following factors:

  - The lateral dimensions of estuary flows are typically much greater than the vertical dimensions. This limits the effectiveness of geometric multigrid, which is the de facto solver approach and is built into solving projection equations across multi-level grids.

  - Along the same lines, this type of domain would lend itself to high-aspect ratio cells, where the vertical cell size is much smaller than the lateral size. However, the geometric multigrid approach also struggles with that.

  - The recommended approach for two-phase simulations in AMR-Wind is to keep the cell size uniform across the air-water interface. With such a large interface and a need for refinements at different bathymetrical features or turbine sites, this may be difficult to conform to, which will bring solver convergence challenges.

Data needs for milestone case

- Bathymetry

- FVCOM data for input, initial condition

- Field measurements for validation

- FVCOM data for comparison of advantages, disadvantages

- Generic underwater turbine, potentially with additional structures

Additional work, aside from completion of milestone run, mentioned in milestone

- Gather information about state of the art to motivate our approach

- Identify post-processing needs and inputs for milestone run in order to do analysis and comparison

- Analyze flow features, quantities of interest, insights about turbine siting within milestone run

- Compare to state-of-the-art modeling options, e.g., FVCOM

Task list – potential assignment [timing]

- Refactor boundary plane implementation in AMR-Wind to be used outside of ABL physics – Michael [April 9]

- Write tool to convert FVCOM data to boundary plane format used for time- and space-varying input to AMR-Wind – Matt [April 30]

- Implement phase-aware and terrain-aware options for boundary plane fill (adapt from ocean waves fill) – Michael [April 30]

- Implement two-phase initialization that reads in an initial state for the flow; potentially also could calculate a reasonable starting point – Michael, Bruce, or Dave [April 30]

- Get bathymetry data into format readable by AMR-Wind [April 30]

- IBFM single-phase verification: laminar flat case [April 30]

- Set up test bed, based on rough estimations of Rosario Strait, to evaluate solver sensitivity to concerns. Expecting flow (FVCOM data) to be less important than domain details (bathymetry data) [April 30]

- Use test bed to evaluate solver concerns: domain aspect ratio, cell aspect ratio, location of refinements [April 30 - July 31]

- IBFM single-phase validation: turbulent flat case (ABL) [May 31]

- IBFM single-phase validation: laminar non-flat case (likely a code-to-code comparison) [May 31]

- IBFM two-phase validation: laminar simple channel [May 31]

- Get FVCOM data for inflow and initial condition [May 31]

- Implement source term needed for validation runs of wall-modeled cases with bathymetry – Michael, Bruce, or Dave [June 30]

- IBFM single-phase validation: turbulent non-flat case (comparison against reference data) [June 30]

- IBFM two-phase validation: turbulent simple channel [June 30]

- IBFM two-phase validation: turbulent realistic channel [June 30]

- Current and sea-surface rise: could be validation or just an exercise to test robustness of implementation [June 30 or July 31]

- Obtain field measurements for validation of milestone case [August 31]

- Define milestone domain, cell resolution, refinement zones, etc. [August 31]

- Define milestone post-processing needs for obtaining QOI, etc. [August 31]

- Run coarse-resolution case with final bathymetry and input data [August 31]

- Understand FVCOM data and state of the art, including limitations [September 30]

- Run full-resolution milestone case with final bathymetry and input data [September 30]

- Compare milestone run data, insights to FVCOM data [September 30]

- Add any required features to AMR-Wind for setting up Kynema model

- Implement added mass capabilities in Kynema aero

- Validate or verify added mass capabilities in Kynema aero

- Get generic underwater turbine specs

- Run milestone case with turbine

Month-by-month focus:

April:

- AMR-Wind features and refactoring, especially for initial and boundary conditions

- The most basic V&V case

- Get bathymetry data

- Set up test bed domain

May:

- Intermediate V&V cases

- Get FVCOM data

- Use test bed, address anything that comes up

June:

- Implement AMR-Wind source term needed for remaining validation cases

- Remaining V&V cases except sea level rise

- Demonstrate / test sea level rise

- Use test bed, address anything that comes up

July:

- Validate sea level rise case if possible

- Use test bed, address anything that comes up

- Finish any tasks left over from May and June

August:

- Define details of milestone run

- Run coarse-resolution milestone case

- Obtain field measurement data for milestone validation

September:

- Run full-resolution milestone case

- Understand state of the art, modeling alternatives

- Analyze milestone results and compare